## Sheet1
Vendor Risk Assessment
| Area Name: | Vendor Onboarding | Updated by: | Carlo Buensalida |  |  | Date Last Updated: | 9/28/2025
[12 empty] | RISK MATRICIES | [6 empty] | Probability | Impact
|  |  |  | Inherent Risk (without controls) |  |  |  |  | Residual Risk (with controls) |  |  | Master Risk Matrix | [6 empty] | Very High | Very High
Unique ID | Risk Description | Caused by & Consequenses | Risk Owner(s) Name and Role | Probabilty | Impact | Risk Rating | Control(s) | Control Owner(s) Name and Role | Residual Probabilty | Residual Impact | Residual Risk Rating | Impact: |  | Very Low | Low | Medium | High | Very High | High | High
VRA0001 | Vendor fails to encrypt customer data at rest | Lack of encryption policy; potential customer data breach & regulatory fines | John Smith – Vendor Security Lead | Very High | Very Low | Moderate | Implement AES-256 encryption for all databases; enable transparent data encryption | Jane Doe – IT Security Manager | Very High | Very Low | Moderate | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | Medium | Medium
VRA0002 | Delayed patching of critical vulnerabilities | Weak patch management schedule; increased exposure to cyberattacks | Maria Lopez – Compliance Officer | High | Very Low | Sustainable | Monthly vulnerability scans; 14-day SLA for patching critical findings | Paul White – Vendor Systems Admin | Low | Very Low | Sustainable |  | High | Sustainable | Moderate | Severe | Critical | Critical | Low | Low
VRA0003 | Inadequate access control for privileged accounts | Shared admin passwords; risk of unauthorized changes | Alex Brown – Operations Head | Medium | High | Severe | Enforce MFA for all privileged accounts; individual accounts for each admin | Sarah Green – Identity & Access Mgmt Lead | Medium | High | Severe |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | Very Low | Very Low
VRA0004 | Third-party subcontractors not screened before onboarding | Missing background checks; risk of insider threats | Nina Torres – Procurement Manager | Low | Medium | Moderate | Standardized vendor due diligence checklist; background verification before contract approval | Chris Lim – Vendor Risk Analyst | Low | Very High | Critical |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical
VRA0005 | Backup data not tested for integrity | Backups performed but never restored/tested; risk of failed recovery | Robert Cruz – Business Continuity Officer | Very Low | Medium | Sustainable | Quarterly backup restore tests with documented results | Emma Tan – Backup & Recovery Specialist | Very Low | Medium | Sustainable |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe
VRA0006 | Absence of documented incident response plan | Uncoordinated response to breaches; extended downtime and loss of trust | Kate Hill – Security & Compliance Manager | Very High | Very High | Critical | Maintain incident response plan and conduct semi-annual tabletop exercises | Brian Cho – Security Operations Lead | Very High | Very Low | Moderate | Inherent Risk Matrix (Before Controls)
VRA0007 | Weak physical security at vendor’s data center | Inadequate badge access; risk of unauthorized physical entry | Michael Reyes – Facilities Manager | Medium | Very Low | Sustainable | Install CCTV & badge access logs; restrict visitor entry | Laura Kim – Physical Security Coordinator | Medium | Very Low | Sustainable | Impact: |  | Very Low | Low | Medium | High | Very High
VRA0008 | Vendor fails to sign updated data processing agreements (DPA) | Legal exposure & noncompliance with privacy laws | Anna Cruz – Legal Counsel | Very Low | Medium | Sustainable | Include mandatory DPA clause in all contracts; automated contract management | Oliver Chan – Legal Contracts Manager | High | Medium | Severe | Probability | Very High | 1 |  |  |  | 1
VRA0009 | Infrequent review of user access | Inactive users remain active; increased insider threat risk | Daniel Ong – HR Lead | Medium | Medium | Moderate | Monthly user access review; automated alerts for inactive accounts | Sophia Liu – HRIS Specialist | Very Low | High | Moderate |  | High | 1
VRA0010 | Disaster Recovery Plan (DRP) not updated after system changes | New systems not covered in DRP; risk of longer downtime during disaster | Sandra Patel – IT Infrastructure Head | Low | Low | Sustainable | Update DRP after major changes; annual DRP test with stakeholders | Kevin Ross – Business Continuity Coordinator | Very Low | Medium | Sustainable |  | Medium | 1 |  | 1 | 1
[13 empty] | Low |  | 1 | 1
[13 empty] | Very Low |  |  | 2
Residual Risk Matrix (After Controls)
[12 empty] | Impact: |  | Very Low | Low | Medium | High | Very High
[12 empty] | Probability | Very High | 2
[13 empty] | High |  |  | 1
[13 empty] | Medium | 1 |  |  | 1
[13 empty] | Low | 1 |  |  |  | 1
[13 empty] | Very Low |  |  | 2 | 1